## Overview
CHUZOSHO WEBSITE TRACKING
Live source of truth for scope, ownership, review, and blockers.
Delivery Summary | Value | Review Summary | Value
Tracked items | 16 | Desktop reviewed | 16
Done | 8 | Mobile reviewed | 16
In progress | 8 | Open issues | 5
Blocked | 0 | High-priority issues | 4
Pending | 0 | Unassigned solution pages | 3
Current decisions
Portfolio | ISLD, IProcure, and IGRC
Solution ownership | One intern per solution; names pending Evan and Sushil
Contact form | Production endpoint pending confirmation from Lokesh
Legal | Adapted from HOSHŌ DIGITAL; internal legal review pending
Daily routine | Update Page Tracking, Daily Updates, and Issues before handover

## Page Tracking
PAGE AND SECTION TRACKING
Record requested changes and verified defects only. Keep desktop and mobile review separate.
Page | Route | Section | Requested Change / Requirement | Status | Owner | Desktop Review | Mobile Review | Priority | Notes / Dependency
Shared | All routes | Header | Standard navigation; Contact Us is a normal navigation link | Done | Evan William | Yes | Yes | High
Shared | All routes | Footer | Consistent type; no Home link; legal and social links; Chuzosho copyright | Done | Evan William | Yes | Yes | High
Home | / | Hero | Full-screen hero with title only | Done | Evan William | Yes | Yes | High
Home | / | Our Philosophy | Straighten image alignment and remove decorative numbering | Done | Evan William | Yes | Yes | Medium
Foundry | /about/ | Hero | Full-screen hero with title only | Done | Evan William | Yes | Yes | High
Approach | /approach/ | Hero and stages | Full-screen hero; no 01/02/03/04 labels | Done | Evan William | Yes | Yes | High
Solutions | /solutions/ | Portfolio | Replace previous products with ISLD, IProcure, and IGRC | Done | Evan William | Yes | Yes | High
Partnership | /partnership/ | B2B channels | Remove Ways to work together eyebrow | Done | Evan William | Yes | Yes | Medium
Contact | /contact/ | Form | No hero; remove Start a conversation; use Submit; add privacy statement | In Progress | Evan William | Yes | Yes | High | Production endpoint pending
ISLD | /solutions/isld/ | Full page | Product page; official expansion and owner approval pending | In Progress | To be assigned | Yes | Yes | High | Confirm official product scope
IProcure | /solutions/iprocure/ | Full page | Product page and procurement positioning | In Progress | To be assigned | Yes | Yes | High | Confirm product scope
IGRC | /solutions/igrc/ | Full page | Product page and governance positioning | In Progress | To be assigned | Yes | Yes | High | Confirm product scope
Legal | /privacy-policy/ | Policy | Adapt HOSHŌ DIGITAL privacy page for Chuzosho | In Progress | Evan William | Yes | Yes | Medium | Internal legal review
Legal | /accessibility/ | Statement | Add accessibility statement | In Progress | Evan William | Yes | Yes | Medium | Internal review
Legal | /terms-of-use/ | Terms | Adapt HOSHŌ DIGITAL terms for Chuzosho | In Progress | Evan William | Yes | Yes | Medium | Internal legal review
Legal | /cookies-policy/ | Policy | Add cookies policy | In Progress | Evan William | Yes | Yes | Medium | Confirm analytics and cookies in production

## Ownership
OWNERSHIP
Assignments remain provisional until Evan William and Sushil Singh confirm them.
Surface | Owner | Reviewer | Scope | Status | Notes
Shared UI | Evan William | Sushil Singh | Header, footer, responsive system | Active
Home | Evan William | Sushil Singh | Home page | Active
Foundry | Evan William | Sushil Singh | About / foundry page | Active
Approach | Evan William | Sushil Singh | Approach page | Active
Solutions | Evan William | Sushil Singh | Solutions landing | Active
Partnership | Evan William | Sushil Singh | Partner page | Active
Contact | Evan William | Sushil Singh / Lokesh Meena | Design and endpoint integration | Endpoint pending
ISLD | To be assigned | Product owner | One intern per solution | Pending assignment | Do not guess acronym expansion
IProcure | To be assigned | Product owner | One intern per solution | Pending assignment
IGRC | To be assigned | Product owner | One intern per solution | Pending assignment
Legal | Evan William | Internal legal review | Privacy, accessibility, terms, cookies | Draft | Adapted from HOSHŌ DIGITAL

## Daily Updates
DAILY UPDATES
Add one concise row for every working day and handover.
Date | Owner | Completed | Decision | Blocker | Next Action | Review Link / Commit
2026-08-31 | Evan William | Rebuilt shared system, tracking, portfolio routes, legal pages, and responsive layouts | Portfolio is ISLD, IProcure, and IGRC | Form endpoint and solution-owner assignment pending | Confirm integration with Lokesh; confirm owners with Sushil

## Assets
ASSET TRACKING
Every production visual must have a source path, alt text, and review status.
Page | Asset | File | Purpose | Alt Text | Optimised | Mobile Crop | Owner
Home | Foundry hero | assets/images/chuzosho-foundry-hero-v1.webp | Hero | Technical product foundry transforming raw inputs into finished systems | Yes | Yes | Evan William
Foundry | Press hero | assets/images/memory-press-original-v1.webp | Hero | Industrial press forming solution material into a product module | Yes | Yes | Evan William
Approach | Inspection hero | assets/images/checked-actions-original-v1.webp | Hero | Controlled inspection line checking proposed actions | Yes | Yes | Evan William
Solutions | Portfolio hero | assets/images/program-proofs-original-v1.webp | Hero | Three precision instruments representing the Chuzosho product portfolio | Yes | Yes | Evan William
Partnership | Market gates hero | assets/images/promotion-gates-original-v1.webp | Hero | A finished product moving through market-readiness gates | Yes | Yes | Evan William
Contact | Foundry background | assets/images/subscription-stack-original-v1.webp | Background |  | Yes | Yes | Evan William

## Issues & Blockers
ISSUES AND BLOCKERS
Record unresolved dependencies instead of inventing content or integrations.
ID | Area | Issue / Dependency | Owner | Priority | Status | Target | Resolution Notes
CHU-001 | Contact | Production form endpoint, recipient, and data-handling flow need confirmation | Lokesh Meena | High | Open | Before live collection | Front-end remains non-submitting until confirmed
CHU-002 | Solutions | Assign one intern each to ISLD, IProcure, and IGRC | Evan William / Sushil Singh | High | Open | Next team allocation
CHU-003 | ISLD | Confirm official acronym expansion and approved product copy | Product owner | High | Open | Before campaign use | Page avoids unapproved expansion
CHU-004 | Legal | Internal legal and privacy review required | Internal reviewer | High | Open | Before policy sign-off | Draft adapted from HOSHŌ DIGITAL
CHU-005 | Deployment | Confirm production operational ownership and monitoring with Lokesh | Lokesh Meena | Medium | Open | Post-deploy

## Theme References
THEME REFERENCES
Approved visual system and reusable implementation constraints.
Category | Token / Rule | Value | Use | Do | Do Not
Colour | Foundry black | #0D0C0A | Dark surfaces and footer | Use for deliberate contrast | Use pure black everywhere
Colour | Warm paper | #F3EEE4 | Primary light surface | Keep warm-neutral pairing | Mix with cool gray defaults
Colour | Signal red | #D43B32 | Focus, primary CTA, small accents | Use once as primary action | Turn navigation CTA into a red block
Type | Primary | Inter / Helvetica Neue / Arial | Headings and body | Keep consistent across pages | Use decorative footer fonts
Type | Technical | IBM Plex Mono / Courier New | Eyebrows and compact labels | Use sparingly | Use decorative 01/02/03/04 numbers
Hero | Marketing pages | 100dvh | Home, Foundry, Approach, Solutions, Partnership, product pages | Title only | Add short descriptions inside hero
Contact | Opening layout | No hero | Direct form experience | Use transparent dark form treatment | Add Start a conversation eyebrow
Responsive | Mobile | Single-column | All complex sections | Preserve 16px body copy | Shrink desktop grids
Images | Alignment | Grid aligned | Editorial and philosophy sections | Keep media level and cropped intentionally | Tilt or float media accidentally

## Review Checklist
REVIEW CHECKLIST
Use for release review on desktop and mobile before deployment.
Area | Check | Desktop | Mobile | Owner | Status | Notes
Navigation | All routes resolve; active state correct; mobile menu usable | Yes | Yes | Evan William | Done
Heroes | Full viewport, title only, no clipped text or media | Yes | Yes | Evan William | Done
Typography | Consistent font, readable scale, no overflow | Yes | Yes | Evan William | Done
Images | All requested images load; crop and alt text reviewed | Yes | Yes | Evan William | Done
Forms | Labels, focus, consent, error state, and button copy reviewed | Yes | Yes | Evan William | In Progress | Endpoint pending
Footer | Solutions, socials, legal links, and copyright are correct | Yes | Yes | Evan William | Done
Accessibility | Keyboard flow, skip link, reduced motion, contrast | Yes | Yes | Evan William | Done
Production | No console errors or failed assets after deploy | Pending | Pending | Evan William | Pending | Run after production deploy